## Roadmap Reference
AI Adoption
30-60-90 day Roadmap
Teams
# | Capability Area | Tool | Capability | Informatica Dev | Databricks Dev | QE / Testers | Data / Requirements Analyst | Java Dev | Orchestration | Infra Team
1 | Foundation | AI DLC | AI DLC Overview | Initial | Initial | Initial | Initial | Initial | Initial | Initial
2 | Foundation | Training | AI fundamentals / onboarding | Initial | Initial | Initial | Initial | Initial | Initial | Initial
3 | Core Copilot – Developer Productivity | GHCP | Install and configure VSCode with GHCP plug-in, GitHub, Databricks | 30 Day | 30 Day | 30 Day | 30 Day | 30 Day | 30 Day | 30 Day
4 | Core Copilot – Developer Productivity | GHCP | Explain complex code | 30 Day | 30 Day | 30 Day |  | 30 Day
5 | Core Copilot – Developer Productivity | GHCP | Unit test creation | 30 Day | 30 Day | 30 Day |  | 30 Day
6 | Core Copilot – Developer Productivity | GHCP | Unit test execution | 30 Day | 30 Day | 30 Day |  | 30 Day
7 | Core Copilot – Developer Productivity | GHCP | Add comments to code | 30 Day | 30 Day |  |  | 30 Day
8 | Core Copilot – Developer Productivity | GHCP | Code quality reviews | 30 Day | 30 Day | 30 Day |  | 30 Day
9 | Core Copilot – Developer Productivity | GHCP | Identify / fix vulnerabilities in code | 30 Day | 30 Day | 30 Day |  | 30 Day | 30 Day
10 | Core Copilot – Developer Productivity | GHCP | Generate code from comments | 30 Day | 30 Day |  |  | 30 Day
11 | Core Copilot – Developer Productivity | GHCP | Generate README documentation | 30 Day | 30 Day |  |  | 30 Day
12 | Core Copilot – Developer Productivity | GHCP | Identify / fix infrastructure vulnerabilities | [5 empty] | 30 Day | 30 Day
13 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Explain complex code | 60 Day | 60 Day
14 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Unit test creation | 60 Day | 60 Day
15 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Unit test execution | 60 Day | 60 Day
16 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Add comments to code | 60 Day | 60 Day
17 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Code quality reviews | 60 Day | 60 Day
18 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Identify / fix vulnerabilities in code | 60 Day | 60 Day
19 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Generate code from comments | 60 Day | 60 Day
20 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Generate README documentation | 60 Day | 60 Day
21 | Agentic Development | GHCP | Create / Utilize Agents - Requirements | 90 Day | 90 Day |  | 60 Day | 60 Day
22 | Agentic Development | GHCP | Create / Utilize Agents - Testing | 90 Day | 90 Day | 60 Day |  | 60 Day
23 | Agentic Development | GHCP | Create / Utilize Agents - Documentation | 90 Day | 90 Day |  | 60 Day | 60 Day
24 | Agentic Development | GHCP | Create / Utilize Agents - Code Review | 90 Day | 90 Day | 60 Day |  | 60 Day
25 | Agentic Development | GHCP | Create / Utilize Agents - CI/CD | 90 Day | 90 Day |  |  | 60 Day | 60 Day | 60 Day
26 | Agentic Development | GHCP | Create / Utilize Agents - Code Development | 90 Day | 90 Day |  |  | 60 Day
27 | Agentic Development | GHCP | Create / Utilize Agents - Vulnerability Remediation | 90 Day | 90 Day | 60 Day |  | 60 Day | 60 Day | 60 Day
28 | Analyst & QA Enablement | Glean / Microsoft 365 Copilot | Test plan / test case creation |  |  | 30 Day
29 | Analyst & QA Enablement | Glean / Microsoft 365 Copilot | Generate validation SQL from source-to-target mappings |  |  | 30 Day | 30 Day
30 | Analyst & QA Enablement | Glean / Microsoft 365 Copilot | Understand current state design |  |  |  | 30 Day
31 | Analyst & QA Enablement | Glean / Microsoft 365 Copilot | Automate data modeling tasks |  |  |  | 30 Day
32 | Analyst & QA Enablement | Glean / Microsoft 365 Copilot | Automate mapping tasks |  |  |  | 30 Day
33 | Analyst & QA Enablement | Glean / Microsoft 365 Copilot | Automate documentation for RAI |  |  | 60 Day

## Training_Material
Training Rollout
# | Module | Target audience | Format | Owner | Planned date | Status | Audience size | Completed | % complete | Notes / link
1 | AI fundamentals | All | Video |  |  | Not started
2 | GHCP VSCode - Workspace Setup | All | Video |  |  | Not started
3 | GitHub Copilot Basics | All | Video |  |  | Not started
4 | Source-to-Target Mappings with AI | Data / Requirements Analysts | Video |  |  | Not started
5 | Training Analysis Tasks and Lab Session | Data / Requirements Analysts | Video |  |  | Not started
6 | Understanding a Data Field using Glean | Data / Requirements Analysts | Video |  |  | Not started
7 | Training Databricks - Genie VSCode | Java / Python PySpark ETL developers | Video |  |  | Not started
8 | Workspace Setup Databricks | Java / Python PySpark ETL developers | Video |  |  | Not started
9 | GitHub Copilot Advance - Part 1 | Java / Python PySpark ETL developers | Video |  |  | Not started
10 | GitHub Copilot Advance - Part 2 | Java / Python PySpark ETL developers | Video |  |  | Not started
11 | Glean Test Strategy | QA / Testers | Video |  |  | Not started
12 | Test Data Creation | QA / Testers | Video |  |  | Not started
13 | Training DX Metrics Tasks | Tech Leads / Agile Leaders / SEPMs | Video |  |  | Not started
14 | Other Additional Training | Optional | Mixed |  |  | Not started

## Tracker
AI Modernization Tracker
ID | # | Capability Area | Tool | Capability | Role | Phase | Due Date | Owner | Status | Started | Completed | Evidence link | Notes | Overdue | Days late
C01-R1 | 1 | Foundation | AI DLC | AI DLC Overview | Informatica Dev | Initial | 2026-08-15 |  | Done
C01-R2 | 1 | Foundation | AI DLC | AI DLC Overview | Databricks Dev | Initial | 2026-08-15 |  | Done
C01-R3 | 1 | Foundation | AI DLC | AI DLC Overview | QE / Testers | Initial | 2026-08-15 |  | Done
C01-R4 | 1 | Foundation | AI DLC | AI DLC Overview | Data / Requirements Analyst | Initial | 2026-08-15 |  | Done
C01-R5 | 1 | Foundation | AI DLC | AI DLC Overview | Java Dev | Initial | 2026-08-15 |  | Done
C01-R6 | 1 | Foundation | AI DLC | AI DLC Overview | Orchestration, Infra | Initial | 2026-08-15 |  | Done
C02-R1 | 2 | Foundation | Training | AI fundamentals / onboarding | Informatica Dev | Initial | 2026-08-15 |  | Done
C02-R2 | 2 | Foundation | Training | AI fundamentals / onboarding | Databricks Dev | Initial | 2026-08-15 |  | Done
C02-R3 | 2 | Foundation | Training | AI fundamentals / onboarding | QE / Testers | Initial | 2026-08-15 |  | Done
C02-R4 | 2 | Foundation | Training | AI fundamentals / onboarding | Data / Requirements Analyst | Initial | 2026-08-15 |  | Done
C02-R5 | 2 | Foundation | Training | AI fundamentals / onboarding | Java Dev | Initial | 2026-08-15 |  | Done
C02-R6 | 2 | Foundation | Training | AI fundamentals / onboarding | Orchestration, Infra | Initial | 2026-08-15 |  | Done
C03-R1 | 3 | Core Copilot – Developer Productivity | GHCP | Install and configure VSCode with GHCP plug-in, GitHub, Databricks | Informatica Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C03-R2 | 3 | Core Copilot – Developer Productivity | GHCP | Install and configure VSCode with GHCP plug-in, GitHub, Databricks | Databricks Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C03-R3 | 3 | Core Copilot – Developer Productivity | GHCP | Install and configure VSCode with GHCP plug-in, GitHub, Databricks | QE / Testers | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C03-R4 | 3 | Core Copilot – Developer Productivity | GHCP | Install and configure VSCode with GHCP plug-in, GitHub, Databricks | Data / Requirements Analyst | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C03-R5 | 3 | Core Copilot – Developer Productivity | GHCP | Install and configure VSCode with GHCP plug-in, GitHub, Databricks | Java Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C03-R6 | 3 | Core Copilot – Developer Productivity | GHCP | Install and configure VSCode with GHCP plug-in, GitHub, Databricks | Orchestration, Infra | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C04-R1 | 4 | Core Copilot – Developer Productivity | GHCP | Explain complex code | Informatica Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C04-R2 | 4 | Core Copilot – Developer Productivity | GHCP | Explain complex code | Databricks Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C04-R3 | 4 | Core Copilot – Developer Productivity | GHCP | Explain complex code | QE / Testers | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C04-R5 | 4 | Core Copilot – Developer Productivity | GHCP | Explain complex code | Java Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C05-R1 | 5 | Core Copilot – Developer Productivity | GHCP | Unit test creation | Informatica Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C05-R2 | 5 | Core Copilot – Developer Productivity | GHCP | Unit test creation | Databricks Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C05-R3 | 5 | Core Copilot – Developer Productivity | GHCP | Unit test creation | QE / Testers | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C05-R5 | 5 | Core Copilot – Developer Productivity | GHCP | Unit test creation | Java Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C06-R1 | 6 | Core Copilot – Developer Productivity | GHCP | Unit test execution | Informatica Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C06-R2 | 6 | Core Copilot – Developer Productivity | GHCP | Unit test execution | Databricks Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C06-R3 | 6 | Core Copilot – Developer Productivity | GHCP | Unit test execution | QE / Testers | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C06-R5 | 6 | Core Copilot – Developer Productivity | GHCP | Unit test execution | Java Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C07-R1 | 7 | Core Copilot – Developer Productivity | GHCP | Add comments to code | Informatica Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C07-R2 | 7 | Core Copilot – Developer Productivity | GHCP | Add comments to code | Databricks Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C07-R5 | 7 | Core Copilot – Developer Productivity | GHCP | Add comments to code | Java Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C08-R1 | 8 | Core Copilot – Developer Productivity | GHCP | Code quality reviews | Informatica Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C08-R2 | 8 | Core Copilot – Developer Productivity | GHCP | Code quality reviews | Databricks Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C08-R3 | 8 | Core Copilot – Developer Productivity | GHCP | Code quality reviews | QE / Testers | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C08-R5 | 8 | Core Copilot – Developer Productivity | GHCP | Code quality reviews | Java Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C09-R1 | 9 | Core Copilot – Developer Productivity | GHCP | Identify / fix vulnerabilities in code | Informatica Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C09-R2 | 9 | Core Copilot – Developer Productivity | GHCP | Identify / fix vulnerabilities in code | Databricks Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C09-R3 | 9 | Core Copilot – Developer Productivity | GHCP | Identify / fix vulnerabilities in code | QE / Testers | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C09-R5 | 9 | Core Copilot – Developer Productivity | GHCP | Identify / fix vulnerabilities in code | Java Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C09-R6 | 9 | Core Copilot – Developer Productivity | GHCP | Identify / fix vulnerabilities in code | Orchestration, Infra | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C10-R1 | 10 | Core Copilot – Developer Productivity | GHCP | Generate code from comments | Informatica Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C10-R2 | 10 | Core Copilot – Developer Productivity | GHCP | Generate code from comments | Databricks Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C10-R5 | 10 | Core Copilot – Developer Productivity | GHCP | Generate code from comments | Java Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C11-R1 | 11 | Core Copilot – Developer Productivity | GHCP | Generate README documentation | Informatica Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C11-R2 | 11 | Core Copilot – Developer Productivity | GHCP | Generate README documentation | Databricks Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C11-R5 | 11 | Core Copilot – Developer Productivity | GHCP | Generate README documentation | Java Dev | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C12-R6 | 12 | Core Copilot – Developer Productivity | GHCP | Identify / fix infrastructure vulnerabilities | Orchestration, Infra | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C13-R1 | 13 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Explain complex code | Informatica Dev | 60 Day | 2026-09-30 |  | Not started
C14-R1 | 14 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Unit test creation | Informatica Dev | 60 Day | 2026-09-30 |  | Not started
C15-R1 | 15 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Unit test execution | Informatica Dev | 60 Day | 2026-09-30 |  | Not started
C16-R1 | 16 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Add comments to code | Informatica Dev | 60 Day | 2026-09-30 |  | Not started
C17-R1 | 17 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Code quality reviews | Informatica Dev | 60 Day | 2026-09-30 |  | Not started
C18-R1 | 18 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Identify / fix vulnerabilities in code | Informatica Dev | 60 Day | 2026-09-30 |  | Not started
C19-R1 | 19 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Generate code from comments | Informatica Dev | 60 Day | 2026-09-30 |  | Not started
C20-R1 | 20 | Databricks Genie – Platform-Native Assist | Databricks / Genie | Generate README documentation | Informatica Dev | 60 Day | 2026-09-30 |  | Not started
C21-R1 | 21 | Agentic Development | GHCP | Create / Utilize Agents - Requirements | Informatica Dev | 90 Day | 2026-10-30 |  | Not started
C21-R2 | 21 | Agentic Development | GHCP | Create / Utilize Agents - Requirements | Databricks Dev | 60 Day | 2026-09-30 |  | Not started
C21-R4 | 21 | Agentic Development | GHCP | Create / Utilize Agents - Requirements | Data / Requirements Analyst | 60 Day | 2026-09-30 |  | Not started
C21-R5 | 21 | Agentic Development | GHCP | Create / Utilize Agents - Requirements | Java Dev | 60 Day | 2026-09-30 |  | Not started
C22-R1 | 22 | Agentic Development | GHCP | Create / Utilize Agents - Testing | Informatica Dev | 90 Day | 2026-10-30 |  | Not started
C22-R2 | 22 | Agentic Development | GHCP | Create / Utilize Agents - Testing | Databricks Dev | 60 Day | 2026-09-30 |  | Not started
C22-R3 | 22 | Agentic Development | GHCP | Create / Utilize Agents - Testing | QE / Testers | 60 Day | 2026-09-30 |  | Not started
C22-R5 | 22 | Agentic Development | GHCP | Create / Utilize Agents - Testing | Java Dev | 60 Day | 2026-09-30 |  | Not started
C23-R1 | 23 | Agentic Development | GHCP | Create / Utilize Agents - Documentation | Informatica Dev | 90 Day | 2026-10-30 |  | Not started
C23-R2 | 23 | Agentic Development | GHCP | Create / Utilize Agents - Documentation | Databricks Dev | 60 Day | 2026-09-30 |  | Not started
C23-R4 | 23 | Agentic Development | GHCP | Create / Utilize Agents - Documentation | Data / Requirements Analyst | 60 Day | 2026-09-30 |  | Not started
C23-R5 | 23 | Agentic Development | GHCP | Create / Utilize Agents - Documentation | Java Dev | 60 Day | 2026-09-30 |  | Not started
C24-R1 | 24 | Agentic Development | GHCP | Create / Utilize Agents - Code Review | Informatica Dev | 90 Day | 2026-10-30 |  | Not started
C24-R2 | 24 | Agentic Development | GHCP | Create / Utilize Agents - Code Review | Databricks Dev | 60 Day | 2026-09-30 |  | Not started
C24-R3 | 24 | Agentic Development | GHCP | Create / Utilize Agents - Code Review | QE / Testers | 60 Day | 2026-09-30 |  | Not started
C24-R5 | 24 | Agentic Development | GHCP | Create / Utilize Agents - Code Review | Java Dev | 60 Day | 2026-09-30 |  | Not started
C25-R1 | 25 | Agentic Development | GHCP | Create / Utilize Agents - CI/CD | Informatica Dev | 90 Day | 2026-10-30 |  | Not started
C25-R2 | 25 | Agentic Development | GHCP | Create / Utilize Agents - CI/CD | Databricks Dev | 60 Day | 2026-09-30 |  | Not started
C25-R5 | 25 | Agentic Development | GHCP | Create / Utilize Agents - CI/CD | Java Dev | 60 Day | 2026-09-30 |  | Not started
C25-R6 | 25 | Agentic Development | GHCP | Create / Utilize Agents - CI/CD | Orchestration, Infra | 60 Day | 2026-09-30 |  | Not started
C26-R1 | 26 | Agentic Development | GHCP | Create / Utilize Agents - Code Development | Informatica Dev | 90 Day | 2026-10-30 |  | Not started
C26-R2 | 26 | Agentic Development | GHCP | Create / Utilize Agents - Code Development | Databricks Dev | 60 Day | 2026-09-30 |  | Not started
C26-R5 | 26 | Agentic Development | GHCP | Create / Utilize Agents - Code Development | Java Dev | 60 Day | 2026-09-30 |  | Not started
C27-R1 | 27 | Agentic Development | GHCP | Create / Utilize Agents - Vulnerability Remediation | Informatica Dev | 90 Day | 2026-10-30 |  | Not started
C27-R2 | 27 | Agentic Development | GHCP | Create / Utilize Agents - Vulnerability Remediation | Databricks Dev | 60 Day | 2026-09-30 |  | Not started
C27-R3 | 27 | Agentic Development | GHCP | Create / Utilize Agents - Vulnerability Remediation | QE / Testers | 60 Day | 2026-09-30 |  | Not started
C27-R5 | 27 | Agentic Development | GHCP | Create / Utilize Agents - Vulnerability Remediation | Java Dev | 60 Day | 2026-09-30 |  | Not started
C27-R6 | 27 | Agentic Development | GHCP | Create / Utilize Agents - Vulnerability Remediation | Orchestration, Infra | 60 Day | 2026-09-30 |  | Not started
C28-R3 | 28 | Analyst & QA Enablement | Glean / Microsoft 365 Copilot | Test plan / test case creation | QE / Testers | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C29-R3 | 29 | Analyst & QA Enablement | Glean / Microsoft 365 Copilot | Generate validation SQL from source-to-target mappings | QE / Testers | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C29-R4 | 29 | Analyst & QA Enablement | Glean / Microsoft 365 Copilot | Generate validation SQL from source-to-target mappings | Data / Requirements Analyst | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C30-R4 | 30 | Analyst & QA Enablement | Glean / Microsoft 365 Copilot | Understand current state design | Data / Requirements Analyst | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C31-R4 | 31 | Analyst & QA Enablement | Glean / Microsoft 365 Copilot | Automate data modeling tasks | Data / Requirements Analyst | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C32-R4 | 32 | Analyst & QA Enablement | Glean / Microsoft 365 Copilot | Automate mapping tasks | Data / Requirements Analyst | 30 Day | 2026-08-31 |  | Not started |  |  |  |  | Overdue | 30
C33-R3 | 33 | Analyst & QA Enablement | Glean / Microsoft 365 Copilot | Automate documentation for RAI | QE / Testers | 60 Day | 2026-09-30 |  | Not started
Formulas:
Due Date = INDEX(Settings!$C11:C14,MATCH([Phase],Settings!$A11:A14,0))

## Evidence (hidden)
Evidence to Retain
What we collect to show adoption at Day 90.
# | Evidence | Owner | Status | Examples collected | Where it lives (link) | Notes
1 | Training completion |  | Not started
2 | Sample use cases |  | Not started
3 | Generated test cases |  | Not started
4 | Code-review examples |  | Not started
5 | Documentation examples |  | Not started
6 | Approved AI usage examples |  | Not started

## Settings (hidden)
Settings
Yellow cells are inputs. Everything else calculates from them.
Program start (Day 0) | 2026-08-01
Today | 2026-09-30
Program day | 60
Current phase | 60 Day
Phase | Due on day | Due date | Focus
Initial | 14 | 2026-08-15 | AI DLC overview and AI fundamentals for everyone.
30 Day | 30 | 2026-08-31 | AI fundamentals, tool setup, code assistance, testing, documentation and basic security use cases.
60 Day | 60 | 2026-09-30 | Databricks / Genie, broader AI-assisted delivery and initial agent use cases.
90 Day | 90 | 2026-10-30 | Advanced agent-based use cases and deeper automation across the delivery lifecycle.
Status values |  | Meaning
Not started |  | Default
In progress |  | Some of the role has started using it
Done |  | Whole role uses it in real work
Blocked |  | Access, tooling or time issue — add a note
N/A |  | Descoped for this team
Formulas:
Due date = B4+[Due on day]
Note on B4: Given by Nilabh: program started 1 Aug 2026.
Note on B11: Assumption: the workbook gives no date for 'Initial'. Set to Day 14; change if needed.

## Dashboard (hidden)
AI Modernization Plan — Dashboard
All figures calculate from the Tracker, Training and Evidence tabs. Nothing to edit here.
Program day |  | Current phase |  | Overall % done |  | Overdue items |  | Blocked items |  | Training modules rolled out
60 of 90 |  | 60 Day |  | 13.04% |  | 43 |  | 0 |  | 0 of 14
By phase
Phase | Due date | Items | Done | In progress | Blocked | Not started | N/A | % done | Overdue
Initial | 2026-08-15 | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 0
30 Day | 2026-08-31 | 43 | 0 | 0 | 0 | 43 | 0 | 0% | 43
60 Day | 2026-09-30 | 30 | 0 | 0 | 0 | 30 | 0 | 0% | 0
90 Day | 2026-10-30 | 7 | 0 | 0 | 0 | 7 | 0 | 0% | 0
Total |  | 92 | 12 | 0 | 0 | 80 | 0 | 13.04% | 43
By role
Role | Due date | Items | Done | In progress | Blocked | Not started | N/A | % done | Overdue
Informatica Dev | — | 26 | 2 | 0 | 0 | 24 | 0 | 7.692% | 9
Databricks Dev | — | 18 | 2 | 0 | 0 | 16 | 0 | 11.11% | 9
QE / Testers | — | 14 | 2 | 0 | 0 | 12 | 0 | 14.29% | 8
Data / Requirements Analyst | — | 9 | 2 | 0 | 0 | 7 | 0 | 22.22% | 5
Java Dev | — | 18 | 2 | 0 | 0 | 16 | 0 | 11.11% | 9
Orchestration | — | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
Total |  | 85 | 10 | 0 | 0 | 75 | 0 | 11.76% | 40
How to use: leads update the Status column on the Tracker tab weekly. Overdue = past the phase due date and not Done/N/A. Change Day 0 or phase days on Settings.
Formulas:
Due date = INDEX(Settings!$C11:C14,MATCH([Program day],Settings!$A11:A14,0))